## Sheet1
Chat Application Progress Sheet – B80
Day	Date	Task Assigned	Status
1	20-04-2016	Prepare the requirements for the applicaton.	Submitted the requirement document an hour late as per the schedule.
2	21-04-2016	1.Preare the High level design document. 2.Modify the requirement document with minor changes. / 3. Complete the individual tasks assigned to each member in the group.	1. The HDL was done and document preparation was in progress, will be submitted Tomorrow , 22-04-2016. / 2. Modified the SRS document and submitted Today. / 3. In Progress, Python learning was in progress, Two way chat program was completed.
3	22-04-2016	1.Modify the requirement document with minor changes. / 2.Prepare and send the HLD document.	1. Modified the SRS document and submitted Today. / 2. Completed the HLD document and submitted.
4	25-04-2015	1.Finalise the requirement document. / 2.Modify and send the HLD document.	1. Modified and finalised the SRS document and submitted. / 2. Updated the HLD document and submitted.
5	26-04-2014	1.Finalise the HLD document. / 2.Finish the individual task's assigned. / 3.Start preparing LLD document.	1. Modified the HLD document and submitted. / 2. Individual tasks were in progress / 3. Started preaparing LLD.
6	27-04-2013	1. Prepare Event manager document. / 2. Prepare the functions for each event.	1.Prepared the Event manager document and submited. / 2.Functions preparation was in progress.
7	28-04-2013	1.Finalise both HLD and LLD, Event document and all the functions.	1.Finished all the required documents.